FOUNDER OS

Cash Flow Machine

Campaign Brief

# Campaign Brief -- The Cash Flow Machine (Cohort #1)

Document Owner: Matt Gray

Last Updated: April 8, 2026

Launch Date: May 29, 2026

Enrollment Close: May 15, 2026

## Executive Summary

The Cash Flow Machine is a 14-day live cohort (6 sessions, MWF, 90 min each) for founders doing $20K-$500K+/month who have revenue but lack predictable cash flow, healthy margins, and scalable systems.

Offer: $800 standard / VIP tier (pricing TBD, likely $1,500-$2,000)

Capacity: 300 seats (100 VIP)

Instructor: Matt Gray (live, every session)

Upsell target: Founder OS Velocity ($29K PIF / $36K plan)

Revenue target: $240K gross (300 x $800) + VIP upside + Velocity conversions

This is Cohort #1. The primary goals are: fill the room, deliver a transformational experience, and convert 15-25% of attendees into Velocity within 30 days post-cohort.

## 8-Day Sprint Timeline

The sprint runs May 7 - May 14 (enrollment close May 15, cohort starts May 29).

All assets must be complete and reviewed by May 6 EOD to allow one day of buffer before the sprint begins.

| Day | Date | Milestone | Owner |

| 0 | May 6 | All assets complete. Final review. | All |

| 1 | May 7 | Landing page live on Webflow. Payment integration tested. | Matthew (Webflow), Don (HubSpot) |

| 2 | May 8 | Hero video filmed, edited, uploaded. Landing page video embed live. | Matt (filming), Yan (edit) |

| 3 | May 9 | Email sequences loaded into HubSpot. Automation workflows built and tested. | Don (HubSpot), Bhea (Kajabi) |

| 4 | May 10 | Organic launch: Matt posts announcement (IG Story, Reels, LinkedIn, X). Email blast #1 to full list. | Matt (content), Don (email blast) |

| 5 | May 11 | Follow-up content: case study posts (Ali Abdaal, Alex Ikonn). Email blast #2 (testimonial angle). | Matt (content), Don (email) |

| 6 | May 12 | YouTube case study videos go live with case study throw CTAs. Email blast #3 (scarcity). | Matt (video), Don (email) |

| 7 | May 13 | Final push: IG Live or Twitter Space Q&A. Email blast #4 (last chance). | Matt (live), Don (email) |

| 8 | May 14 | Enrollment closes 11:59 PM ET. Final stragglers email. Cart close. | Don (HubSpot) |

Post-enrollment (May 15-28): Pre-cohort onboarding emails fire automatically (5-email sequence already built).

## Task Breakdown by Owner

### Copy (Matt + Claude Code)

• [x] Landing page copy (hero, pain blocks, promise, sessions, pricing, FAQ, CTA)

• [x] Email sequences: pre-launch (4 emails), post-sell onboarding (5 emails), in-cohort (6 emails), post-cohort ascension (4 emails)

• [x] Video scripts (5 scripts: hero, course intro, 2 case study throws, Session 6 bonus)

• [ ] Social media captions for launch week (8-10 posts across IG, LinkedIn, X)

• [ ] Ad copy if running paid (not planned for Cohort #1 -- organic only)

### Matthew / Webflow

• [ ] Build landing page from copy.md spec

• [ ] Mobile responsive QA

• [ ] Payment integration (Stripe checkout or Kajabi redirect)

• [ ] Thank you page / redirect to Kajabi enrollment

• [ ] Hero video embed (once filmed)

• [ ] Countdown timer integration (enrollment close date)

### Yan / Design

• [ ] Hero video edit (60-75 sec, tight cuts, captions)

• [ ] Course intro video edit (60-90 sec)

• [ ] Case study throw edits (2 x 60-90 sec)

• [ ] Session 6 bonus edit (7-9 min, intimate feel)

• [ ] Social media graphics for launch week (story templates, carousel covers)

• [ ] Thumbnail for YouTube case study videos

### Bhea / Kajabi

• [ ] Create Cash Flow Machine product in Kajabi

• [ ] Upload Session replays (post-session, within 24 hours each)

• [ ] Community space setup (hot seat submission threads, intro thread)

• [ ] VIP tier configuration (WhatsApp group link, priority hot seat tagging)

• [ ] Worksheet PDF uploads per session

• [ ] Course intro video placement (first thing students see)

### Don / HubSpot

• [ ] Pre-launch email sequence (4 emails) loaded and automated

• [ ] Post-sell onboarding sequence (5 emails) loaded and automated

• [ ] In-cohort email sequence (6 emails) loaded and automated

• [ ] Post-cohort ascension sequence (4 emails) loaded and automated

• [ ] Enrollment tracking: custom property for CFM cohort status

• [ ] VIP vs standard tier segmentation

• [ ] Cart close automation (May 15 11:59 PM ET cutoff)

• [ ] Velocity conversion tracking (post-cohort)

• [ ] Calendar invite automation for all 6 sessions

### Matt / Video

• [ ] Film hero video (60-75 sec)

• [ ] Film course intro video (60-90 sec)

• [ ] Film Ali Abdaal case study throw (60-90 sec)

• [ ] Film Alex Ikonn case study throw (60-90 sec)

• [ ] Film Session 6 bonus (7-9 min) -- this needs a separate, intentional filming session

• [ ] Social media content for launch week (Reels, Stories, LinkedIn posts)

## Offer Structure

### Standard Tier -- $800

• 6 live sessions with Matt (90 min each, MWF over 14 days)

• All session recordings (available within 24 hours)

• 6 implementation worksheets (one per session)

• Community access (hot seat submissions, peer networking)

• 90-day execution plan (built during Session 6)

### VIP Tier -- $TBD ($1,500 - $2,000 range)

Everything in Standard, plus:

• 2 small-group strategy calls with Matt (intimate, 10-15 people max)

• Personal offer/margin audit by Matt

• WhatsApp group access (direct line to Matt between sessions)

• Priority hot seat selection (every session)

### Revenue Scenarios

| Scenario | Standard | VIP | Gross Revenue |

| Conservative | 200 x $800 | 50 x $1,500 | $235,000 |

| Target | 200 x $800 | 100 x $2,000 | $360,000 |

| Stretch | 250 x $800 | 100 x $2,000 | $400,000 |

Velocity upsell target: 15-25% of cohort (45-75 founders) at $29K-$36K = $1.3M - $2.7M pipeline.

## Copy Requirements

### Landing Page

• Hopkins-level specificity: name the numbers, the timeline, the exact transformation

• Ogilvy brevity: every word earns its place

• Brunson stacking: show what each session delivers, stack the total value

• Hormozi risk reversal: make the $800 feel like a rounding error

• VOC language in pain blocks: pull from actual founder language (DM surveys, call transcripts, intake forms)

• No em dashes

• WCAG 2.1 AA contrast on all text

### Emails

• Subject lines: specific, curiosity-loaded, benefit-driven

• One primary CTA per email

• Emotional specificity: name the feeling, not just the problem

• P.S. lines are the second-most-read part after subject lines

• DFY/Velocity seeding follows the 5-stage progression (subconscious -> warm awareness -> option awareness -> anticipation -> full pitch)

### Video Scripts

• Hero video: stop the scroll, name the pain, make the promise, drive enrollment

• Course intro: eliminate buyer's remorse, set behavioral expectations

• Case study throws: bridge from content to enrollment via specific founder transformations

• Session 6 bonus: Bitmaker story as epiphany bridge, soft Velocity pitch

## Launch Readiness Checklist

### Assets (Complete by May 6)

• [x] Curriculum decks (6 HTML decks, deployed to Vercel)

• [x] Worksheets (6 HTML worksheets with PDF download)

• [x] Email sequences (19 total emails across 4 sequences)

• [x] Video scripts (5 scripts)

• [x] Landing page copy

• [x] Campaign brief (this document)

• [ ] Social media content calendar

• [ ] Graphics package (Yan)

### Infrastructure (Complete by May 7)

• [ ] Landing page live (Webflow)

• [ ] Payment flow tested end-to-end (Stripe/Kajabi)

• [ ] HubSpot automations built and tested

• [ ] Kajabi product created and configured

• [ ] Zoom sessions scheduled (6 sessions, calendar invites ready)

• [ ] Community space created and configured

• [ ] VIP WhatsApp group created

### Pre-Launch Testing (May 7)

• [ ] Complete one test purchase (standard tier)

• [ ] Complete one test purchase (VIP tier)

• [ ] Verify onboarding email fires immediately

• [ ] Verify calendar invites deliver

• [ ] Verify Kajabi access works

• [ ] Verify community space accessible

• [ ] Mobile responsive check on landing page

• [ ] Load test: landing page performs under traffic

## Key Dates

| Date | Event |

| May 6 | All assets final |

| May 7 | Landing page live, infrastructure complete |

| May 8 | Hero video filmed and edited |

| May 10 | Public launch (organic) |

| May 15 | Enrollment closes 11:59 PM ET |

| May 15-28 | Pre-cohort onboarding sequence fires |

| May 26 | VIP WhatsApp group activates |

| May 29 | Session 1: The Revenue Reset |

| May 31 | Session 2: Offer Compression |

| June 2 | Session 3: Pricing & Margin Expansion |

| June 4 | Session 4: The Lead Engine |

| June 6 | Session 5: Sales Simplification |

| June 9 | Session 6: 90-Day Execution Plan |

| June 9-23 | Post-cohort ascension sequence (Velocity pitch) |

## Open Items

1. VIP pricing: Need to finalize. $1,500 or $2,000? Matt to decide.

2. Session times: Need to lock timezone. Likely 12 PM ET (works for US + some EU).

3. Zoom vs dedicated platform: Zoom for Cohort #1 (simplicity). Evaluate for Cohort #2.

4. Paid ads: Not planned for Cohort #1. Organic fill first. Revisit if under 200 seats by May 12.

5. Social media content calendar: Needs to be built for launch week. Matt + Nick to collaborate.

6. VIP group call dates: Need 2 dates during the 14-day window. Matt to block calendar.

7. Case study permissions: Confirm Ali Abdaal and Alex Ikonn are comfortable being referenced (likely fine -- public info only).

## Team Responsibilities Summary

| Person | Primary Responsibility | Deadline |

| Matt | Video filming, social content, live delivery | May 8 (filming), ongoing (content) |

| Matthew | Webflow landing page build | May 7 |

| Yan | Video editing, graphics | May 9 |

| Bhea | Kajabi setup, replays, community | May 7 |

| Don | HubSpot automations, email loading, tracking | May 7 |

| Nick | Social media strategy support | May 10 |

| Claire | Calendar management, VIP logistics | May 7 |

## Success Metrics

| Metric | Target | Measurement |

| Enrollment | 300 seats | HubSpot + Kajabi |

| VIP enrollment | 100 seats | HubSpot + Kajabi |

| Live attendance (avg) | 70%+ | Zoom reports |

| Hot seat submissions | 50+ per session | Community thread count |

| Community engagement | 80%+ post at least once | Community analytics |

| Velocity conversion (30 days) | 15-25% of cohort | HubSpot pipeline |

| NPS | 70+ | Post-cohort survey |