FOUNDER OS

Social Media Machine

Campaign Brief

# Campaign Brief -- The Social Media Machine (Cohort #2)

Document Owner: Matt Gray

Last Updated: April 8, 2026

Launch Date: June 30, 2026

Enrollment Close: June 16, 2026

## Executive Summary

The Social Media Machine is a 14-day live cohort (6 sessions, MWF, 90 min each) for founders who have real expertise and a business that works but whose content isn't converting, isn't consistent, or isn't systematized.

Offer: $800 standard / VIP tier (pricing TBD, likely $1,500-$2,000)

Capacity: 300 seats (100 VIP)

Instructor: Matt Gray (live, every session)

Upsell target: Founder OS Velocity ($29K PIF / $36K plan)

Revenue target: $240K gross (300 x $800) + VIP upside + Velocity conversions

This is Cohort #2 in the cohort engine (following Cash Flow Machine). Learnings from CFM Cohort #1 (May 29 - June 11) will be incorporated into SMM execution. The 19-day gap between CFM ending and SMM starting allows for iteration.

## 8-Day Sprint Timeline

The sprint runs June 8 - June 15 (enrollment close June 16, cohort starts June 30).

All assets must be complete and reviewed by June 7 EOD to allow one day of buffer.

| Day | Date | Milestone | Owner |

| 0 | June 7 | All assets complete. Final review. | All |

| 1 | June 8 | Landing page live on Webflow. Payment integration tested. | Matthew (Webflow), Don (HubSpot) |

| 2 | June 9 | Hero video filmed, edited, uploaded. Landing page video embed live. | Matt (filming), Yan (edit) |

| 3 | June 10 | Email sequences loaded into HubSpot. Automation workflows built and tested. | Don (HubSpot), Bhea (Kajabi) |

| 4 | June 11 | Organic launch: Matt posts announcement. Email blast #1 to full list. CFM cohort just ended -- leverage momentum. | Matt (content), Don (email blast) |

| 5 | June 12 | Follow-up content: case study posts (Waterfall founder, 100K follower founder). Email blast #2. | Matt (content), Don (email) |

| 6 | June 13 | YouTube case study videos go live with case study throw CTAs. Email blast #3 (scarcity). | Matt (video), Don (email) |

| 7 | June 14 | Final push: IG Live or Twitter Space Q&A. Email blast #4 (last chance). | Matt (live), Don (email) |

| 8 | June 15 | Enrollment closes 11:59 PM ET. Final stragglers email. Cart close. | Don (HubSpot) |

Post-enrollment (June 16-28): Pre-cohort onboarding emails fire automatically (5-email sequence already built).

CFM Cross-Sell Opportunity: Cash Flow Machine graduates receive a targeted email (part of post-cohort ascension) introducing SMM as the content layer that completes their cash flow architecture. "You built the revenue engine. Now build the content machine that feeds it."

## Task Breakdown by Owner

### Copy (Matt + Claude Code)

• [x] Landing page copy (hero, pain blocks, promise, sessions, pricing, FAQ, CTA)

• [x] Email sequences: pre-cohort onboarding (5 emails)

• [x] Video scripts (5 scripts: hero, course intro, 2 case study throws, Session 6 bonus)

• [ ] Pre-launch email sequence (4 emails)

• [ ] In-cohort email sequence (6 emails)

• [ ] Post-cohort ascension sequence (4 emails)

• [ ] Social media captions for launch week (8-10 posts)

• [ ] CFM graduate cross-sell email (1 email)

### Matthew / Webflow

• [ ] Build landing page from copy.md spec (can reuse CFM page structure)

• [ ] Mobile responsive QA

• [ ] Payment integration (Stripe checkout or Kajabi redirect)

• [ ] Thank you page / redirect to Kajabi enrollment

• [ ] Hero video embed

• [ ] Countdown timer integration (enrollment close date)

### Yan / Design

• [ ] Hero video edit (60-75 sec)

• [ ] Course intro video edit (60-90 sec)

• [ ] Case study throw edits (2 x 60-90 sec)

• [ ] Session 6 bonus edit (7-9 min)

• [ ] Social media graphics for launch week

• [ ] YouTube thumbnails

### Bhea / Kajabi

• [ ] Create Social Media Machine product in Kajabi

• [ ] Upload session replays (post-session, within 24 hours)

• [ ] Community space setup

• [ ] VIP tier configuration

• [ ] Worksheet PDF uploads per session

• [ ] Course intro video placement

### Don / HubSpot

• [ ] Pre-launch email sequence loaded and automated

• [ ] Pre-cohort onboarding sequence loaded and automated

• [ ] In-cohort email sequence loaded and automated

• [ ] Post-cohort ascension sequence loaded and automated

• [ ] CFM graduate cross-sell email

• [ ] Enrollment tracking: custom property for SMM cohort status

• [ ] VIP vs standard tier segmentation

• [ ] Cart close automation (June 16 11:59 PM ET)

• [ ] Velocity conversion tracking (post-cohort)

• [ ] Calendar invite automation for all 6 sessions

### Matt / Video

• [ ] Film hero video (60-75 sec)

• [ ] Film course intro video (60-90 sec)

• [ ] Film waterfall case study throw (60-90 sec)

• [ ] Film brand foundation case study throw (60-90 sec)

• [ ] Film Session 6 bonus (7-9 min)

• [ ] Social media content for launch week

## Offer Structure

### Standard Tier -- $800

• 6 live sessions with Matt (90 min each, MWF over 14 days)

• All session recordings (available within 24 hours)

• 6 implementation worksheets (one per session)

• Community access (hot seat submissions, peer networking, content feedback)

• 90-day content plan (built during Session 6)

### VIP Tier -- $TBD ($1,500 - $2,000 range)

Everything in Standard, plus:

• 2 small-group content strategy calls with Matt (10-15 people max)

• Personal brand audit by Matt (positioning, content pillars, hook review)

• WhatsApp group access (direct line to Matt between sessions)

• Priority hot seat selection (every session)

• Matt personally reviews your Brand Foundation worksheet

### Revenue Scenarios

| Scenario | Standard | VIP | Gross Revenue |

| Conservative | 200 x $800 | 50 x $1,500 | $235,000 |

| Target | 200 x $800 | 100 x $2,000 | $360,000 |

| Stretch | 250 x $800 | 100 x $2,000 | $400,000 |

Velocity upsell target: 15-25% of cohort (45-75 founders) at $29K-$36K = $1.3M - $2.7M pipeline.

## Copy Requirements

### Landing Page

• Lead with the architecture framing: "Your content isn't converting because it lacks architecture, not creativity"

• VOC language: "I'm posting but nothing happens," "I don't know what to post," "content takes too long," "I have followers but no clients"

• Stack the value of each session with specific deliverables

• Hormozi risk reversal: $800 for a complete content machine vs. $5K+/month for a content agency

• No em dashes, WCAG 2.1 AA contrast

### Emails

• Subject lines: specific, curiosity-loaded, benefit-driven

• One primary CTA per email

• DFY/Velocity seeding follows the 5-stage progression

• CFM cross-sell email: bridge from cash flow architecture to content architecture naturally

### Video Scripts

• Hero video: name the content frustration, reframe as architecture problem, make the promise

• Course intro: set identity ("you're a Social Media Machine founder"), eliminate buyer's remorse

• Case study throws: specific transformations (2 posts/month to 38, 100K followers to $100K revenue)

• Session 6 bonus: Matt's own content journey as epiphany bridge, soft Velocity pitch

## Launch Readiness Checklist

### Assets (Complete by June 7)

• [x] Curriculum decks (6 HTML decks, deployed to Vercel)

• [x] Worksheets (6 HTML worksheets with PDF download)

• [x] Pre-cohort onboarding emails (5 emails)

• [x] Video scripts (5 scripts)

• [x] Landing page copy

• [x] Campaign brief (this document)

• [ ] Pre-launch email sequence (4 emails)

• [ ] In-cohort email sequence (6 emails)

• [ ] Post-cohort ascension sequence (4 emails)

• [ ] Social media content calendar

• [ ] Graphics package (Yan)

### Infrastructure (Complete by June 8)

• [ ] Landing page live (Webflow)

• [ ] Payment flow tested end-to-end

• [ ] HubSpot automations built and tested

• [ ] Kajabi product created and configured

• [ ] Zoom sessions scheduled (6 sessions, calendar invites ready)

• [ ] Community space created and configured

• [ ] VIP WhatsApp group created

### Pre-Launch Testing (June 8)

• [ ] Complete one test purchase (standard tier)

• [ ] Complete one test purchase (VIP tier)

• [ ] Verify onboarding email fires immediately

• [ ] Verify calendar invites deliver

• [ ] Verify Kajabi access works

• [ ] Verify community space accessible

• [ ] Mobile responsive check on landing page

## Key Dates

| Date | Event |

| June 7 | All assets final |

| June 8 | Landing page live, infrastructure complete |

| June 9 | Hero video filmed and edited |

| June 11 | Public launch (organic) -- same day CFM Cohort #1 ends |

| June 16 | Enrollment closes 11:59 PM ET |

| June 16-28 | Pre-cohort onboarding sequence fires |

| June 27 | VIP WhatsApp group activates |

| June 30 | Session 1: The Brand Foundation |

| July 2 | Session 2: The Content GPS |

| July 4 | Session 3: The Hook Engine |

| July 7 | Session 4: The Content Waterfall |

| July 9 | Session 5: The Distribution Machine |

| July 11 | Session 6: The 90-Day Content Plan |

| July 11-25 | Post-cohort ascension sequence (Velocity pitch) |

## Open Items

1. VIP pricing: Align with CFM VIP pricing. Same tier, same price, same perks structure.

2. Session times: Match CFM timing for consistency. Likely 12 PM ET.

3. CFM cross-sell: Draft the bridge email from CFM graduates to SMM. Natural narrative: "You built the engine. Now build the fuel."

4. July 4 session: Session 3 falls on US Independence Day. Consider moving to July 3 or July 5. Need to decide before calendar invites go out.

5. Case study permissions: Source real founder stories for the case study throws. Waterfall and Brand Foundation transformations. Can anonymize if needed.

6. Content vs. CFM differentiation: Landing page must clearly differentiate SMM from CFM for founders who saw both. CFM = revenue architecture. SMM = content architecture. Together they're the full system.

7. CFM testimonial leverage: If CFM Cohort #1 generates strong testimonials by June 11, incorporate them into SMM launch emails.

## Team Responsibilities Summary

| Person | Primary Responsibility | Deadline |

| Matt | Video filming, social content, live delivery | June 9 (filming), ongoing (content) |

| Matthew | Webflow landing page build (can template from CFM) | June 8 |

| Yan | Video editing, graphics | June 10 |

| Bhea | Kajabi setup, replays, community | June 8 |

| Don | HubSpot automations, email loading, tracking | June 8 |

| Nick | Social media strategy support, content calendar | June 11 |

| Claire | Calendar management, VIP logistics | June 8 |

## Success Metrics

| Metric | Target | Measurement |

| Enrollment | 300 seats | HubSpot + Kajabi |

| VIP enrollment | 100 seats | HubSpot + Kajabi |

| CFM graduate conversion | 20%+ of CFM cohort enrolls in SMM | HubSpot |

| Live attendance (avg) | 70%+ | Zoom reports |

| Hot seat submissions | 50+ per session | Community thread count |

| Community engagement | 80%+ post at least once | Community analytics |

| Velocity conversion (30 days) | 15-25% of cohort | HubSpot pipeline |

| NPS | 70+ | Post-cohort survey |

## Learnings to Incorporate from CFM Cohort #1

*This section will be populated after CFM Cohort #1 completes (June 11). Key areas to evaluate:*

• What enrollment velocity looked like (front-loaded vs. last-minute)

• Which email drove the most enrollments

• Live attendance rates by session

• Hot seat submission volume and quality

• Community engagement patterns

• VIP tier conversion rate and satisfaction

• Session 6 Velocity pitch conversion rate

• Any operational issues (Zoom, Kajabi, calendar invites)